## Sheet3
WBS/ID | Deliverable/Task | Description | Owner | Acceptance Criteria | Est(hrs) | Dependency | Due | Status
1 | Planning & Setup
1.1 | Choose sample app (Node/Express) |  | Me |  | 0.5 | - | 2025-08-25 | To Do
1.2 | Repo + branch strategy |  | Me |  | 0.5 | 1.1 | 2025-08-25 | To Do
1.3 | Define success criteria |  | Me |  | 0.5 | 1.2 | 2025-08-25 | To Do
2 | Containerization | [6 empty] | To Do
2.1 | Write Dockerfile |  | Me |  | 1 | 1.3 | 2025-08-26 | To Do
2.2 | Run container locally |  | Me |  | 0.5 | 2.1 | 2025-08-26 | To Do
2.3 | Push to Docker Hub |  | Me |  | 0.5 | 2.2 | 2025-08-26 | To Do
3 | CI/CD | [6 empty] | To Do
3.1 | GitHub Actions workflow |  | Me |  | 1.5 | 2.3 | 2025-08-27 | To Do
3.2 | Build + test job |  | Me |  | 1 | 3.1 | 2025-08-27 | To Do
3.3 | Build & push image job |  | Me |  | 1 | 3.2 | 2025-08-27 | To Do
3.4 | Deploy to VM job |  | Me |  | 2 | 3.3 | 2025-08-28 | To Do
4 | Cloud VM | [6 empty] | To Do
4.1 | Provision EC2 free tier |  | Me |  | 1 | 3.1 | 2025-08-27 | To Do
4.2 | Security group (80/8080) |  | Me |  | 0.5 | 4.1 | 2025-08-27 | To Do
4.3 | Bootstrap script (docker + compose) |  | Me |  | 1 | 4.2 | 2025-08-28 | To Do
5 | Monitoring & Logs | [6 empty] | To Do
5.1 | Health check endpoint |  | Me |  | 0.5 | 2.1 | 2025-08-26 | To Do
5.2 | Log rotation notes |  | Me |  | 0.5 | 4.3 | 2025-08-28 | To Do
6 | Documentation | [6 empty] | To Do
6.1 | Architecture diagram |  | Me |  | 1 | 5.2 | 2025-08-29 | To Do
6.2 | Runbook |  | Me |  | 1 | 6.1 | 2025-08-29 | To Do
6.3 | README polish |  | Me |  | 1 | 6.2 | 2025-08-29 | To Do

## Tracker
Task ID | Task | Owner | Priority | Start | End | DurationDays | %Complete | Status | Risk | Notes | WBS ID | DependsOn
1.1 | Choose sample app (Node/Express) | Me | Medium | 2025-08-25 | 2025-08-25 |  | 0 | To Do |  |  | 1.1 | -
1.2 | Repo + branch strategy | Me | Medium | 2025-08-25 | 2025-08-25 | 1 | 0 | To Do |  |  | 1.2 | 1.1
1.3 | Define success criteria | Me | Medium | 2025-08-25 | 2025-08-25 | 1 | 0 | To Do |  |  | 1.3 | 1.2
2.1 | Write Dockerfile | Me | Medium | 2025-08-26 | 2025-08-26 | 1 | 0 | To Do |  |  | 2.1 | 1.3
2.2 | Run container locally | Me | Medium | 2025-08-26 | 2025-08-26 | 1 | 0 | To Do |  |  | 2.2 | 2.1
2.3 | Push to Docker Hub | Me | Medium | 2025-08-26 | 2025-08-26 | 1 | 0 | To Do |  |  | 2.3 | 2.2
3.1 | GitHub Actions workflow | Me | Medium | 2025-08-27 | 2025-08-27 | 1 | 0 | To Do |  |  | 3.1 | 2.3
3.2 | Build + test job | Me | Medium | 2025-08-27 | 2025-08-27 | 1 | 0 | To Do |  |  | 3.2 | 3.1
3.3 | Build & push image job | Me | Medium | 2025-08-27 | 2025-08-27 | 1 | 0 | To Do |  |  | 3.3 | 3.2
3.4 | Deploy to VM job | Me | Medium | 2025-08-28 | 2025-08-28 | 1 | 0 | To Do |  |  | 3.4 | 3.3
4.1 | Provision EC2 free tier | Me | Medium | 2025-08-27 | 2025-08-27 | 1 | 0 | To Do |  |  | 4.1 | 3.1
4.2 | Security group (80/8080) | Me | Medium | 2025-08-27 | 2025-08-27 | 1 | 0 | To Do |  |  | 4.2 | 4.1
4.3 | Bootstrap script (docker + compose) | Me | Medium | 2025-08-28 | 2025-08-28 | 1 | 0 | To Do |  |  | 4.3 | 4.2
5.1 | Health check endpoint | Me | Medium | 2025-08-26 | 2025-08-26 | 1 | 0 | To Do |  |  | 5.1 | 2.1
5.2 | Log rotation notes | Me | Medium | 2025-08-28 | 2025-08-28 | 1 | 0 | To Do |  |  | 5.2 | 4.3
6.1 | Architecture diagram | Me | Medium | 2025-08-29 | 2025-08-29 | 1 | 0 | To Do |  |  | 6.1 | 5.2
6.2 | Runbook | Me | Medium | 2025-08-29 | 2025-08-29 | 1 | 0 | To Do |  |  | 6.2 | 6.1
6.3 | README polish | Me | Medium | 2025-08-29 | 2025-08-29 | 1 | 0 | To Do |  |  | 6.3 | 6.2
Formulas:
DurationDays = NETWORKDAYS([Start],[End])

## Gantt
Task ID – Task | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29
1.1 - Choose sample app (Node/Express) | 1
1.2 - Repo + branch strategy | 1
1.3 - Define success criteria | 1
2.1 - Write Dockerfile |  | 1
2.2 - Run container locally |  | 1
2.3 - Push to Docker Hub |  | 1
3.1 - GitHub Actions workflow |  |  | 1
3.2 - Build + test job |  |  | 1
3.3 - Build & push image job |  |  | 1
3.4 - Deploy to VM job |  |  |  | 1
4.1 - Provision EC2 free tier |  |  | 1
4.2 - Security group (80/8080) |  |  | 1
4.3 - Bootstrap script (docker + compose) |  |  |  | 1
5.1 - Health check endpoint |  | 1
5.2 - Log rotation notes |  |  |  | 1
6.1 - Architecture diagram |  |  |  |  | 1
6.2 - Runbook |  |  |  |  | 1
6.3 - README polish |  |  |  |  | 1